## Sheet1
Target Timelines | Task | Time (Hrs) | Predicted Hours Subtotals | Actual Hours Subtotals | Cost Subtotals ($) | Predicted Total Hours | Actual Total Hours | Total Cost ($)
May 20 2016 | Project Management |  | 18 | 18 | 1800 | 175 | 159 | 17500
Proposal:
| Project Overview | 2
| Budget | 1
| Communication Brief | 2
| Risk Analysis | 1
Protoype Documentation:
| Specs | 5
| Architecture | 2
| Wireframes | 5
May 25 2016 | Design Concept |  | 13 | 6 | 1300
| Creative Brief | 5
| Design Mockups | 8
June 8 2016 | Prototype |  | 144 | 134 | 14400
| Make PDFs accessible | 16
| Put all PDFs in HTML Format | 40
| Closed Captioning for Videos | 16
| Accessible dropdown transcripts for videos | 16
| Mobile Layout | 8
| Tablet Layout | 8
| Desktop Layout | 8
| Functioning Contact Form | 5
| Functioning Search Bar | 10
| Consistent Navigation/Header | 2
| Consistent Footer | 2
| ARIA where needed | 5
| Ensure all accessibility requirements are met | 8